## Arkusz1
REALISED ACTIVITIES AND INVESTMENTS
Status of works on the key investment projects
Investment | Project status |  |  | CAPEX 2015 | Total CAPEX | Work progress | Anticipated date of completion
|  |  |  | [PLN mln] | [PLN mln] | (%)
Construction of a 1,075 MW power unit No. 11 | The following works were completed on the construction site: | •Assembly of the boiler house's main structure | •Assembly of electrostatic precipitator's supporting structure | 1 752.2 | 5 922.0 | 78% | 2017
|  | •Assembly of the machine room’s housing | •Reinforced concrete structures of ash tanks
|  | •Assembly of cooling water pumps | •Performance of reinforced concrete structure of gypsum store
|  | •Assembly of start-up boilers | •Assembly of a stator and rotor
|  | •Assembly of unit, tap and reserve transformers | of the generator
IOS IV flue gas desulphurisation plant | Unit No. 1 was connected to the system of starting flue gas channels and raw and starting flue gas to chimney No. 3 |  |  | 75.1 | 288.3 | 98% | 2016
Tests are in progress within the Start-up Programme. Works connected with chimney No. 3 were completed
and the chimney was commissioned.
Modernisation of unit No. 1 | Modernisation works were completed and test run was successfully completed. |  |  | 91.3 | 91.3 | 100% | 2015
Modernisation of unit No. 2 | Modernisation works were completed and test run was successfully completed. |  |  | 77.0 | 77.0 | 100% | 2015
deNOx installation on boiler No. K8 | The investment was completed. The project is being settled. |  |  | 6.5 | 20.7 | 100% | 2015
Construction of industrial waste and rainwater treatment | Completed: construction of the switching station with new transformers, construction of the sludge thickening station, |  |  | 20.2 | 29.4 | 72% | 2016
3rd line of multi-chamber reactors, reconstruction of S01 pump room, works on V800 reservoir.
Installation of flue gases denitrification - SCR for units No. 1 and 2 | SCR installation on unit No. 2 was commissioned. Unit No. 1 is ready to start-up and functional tests were performed with ammonia water fed to SCR installation on unit No. 1. |  |  | 79.7 | 97.9 | 87% | 2016
Modernisation of unit No. 9 as a part of 2 x 500 MW modernisation programme | In 2017 the modernisation of unit No. 9 is planned. Currently, the material scopes and tender documents are being prepared relating to the works connected with the modernisation of unit No. 9. |  |  | 0 | 130.2 | 1% | 2017
Modernisation of cooling water intake - stabilising checkdam on the Vistula River | The project is at the stage of preparation for realisation. The environmental decision is pending. |  |  | 8.0 | 32.0 | 2% | 2017
Installation of the catalytic denitrogenation of flue gases and modernisation of electrostatic precipitators for AP - 1650 boilers of units No. 9 and 10 as a part of the 2 x 500 MW modernisation programme. | The documents are being prepared which are needed for the conduct of the tender procedure for the selection of a General Contractor who will realise the SCR installation on units No. 9 and 10 and replacement of the electrostatic precipitator |  |  | 1.3 | 302.1 | 6% | 2017
on unit No. 9 and modernisation of the electrostatic precipitator on Unit No. 10.
Installation of flue gases denitrification - SCR for units No. 4-8 | Completion of the SCR installation of flue gases denitrification on units No. 6 and 7 and the common part for SCR installation for units No. 4-8 Some works were also performed relating to the SCR installation on unit No. 4 and 8. Currently, SCR installation on unit No. 5 is being performed. |  |  | 21.4 | 203.7 | 67% | 2017
Installation of flue gases denitrification - SNCR for unit No. 3 | "The analysis of the necessity of the installation of flue gases denitrification on 200 MW unit No. 3" was developed in the light of regulations in force and the other installations of flue gases denitrification in Enea Wytwarzanie, Świerże Górne location. |  |  | 0 | 42.6 | 1% | 2017
Construction of flue gas desulphurisation plant on K7 and K8 boilers | The contractor of the flue gas desulphurisation plant on K7 and K8 boilers was selected. Currently, the basic project is being performed. An agreement was concluded with the National Fund of Environmental Protection and Water Management for the co-financing of the investment as a loan. The Specification of Essential Terms of a Contract was approved and the tender procedure was announced for the Contract Engineer. |  |  | 0.2 | 85.6 | 11% | 2017
Modernisation of unit No. 10 as a part | In 2018 the modernisation of unit No. 10 is planned. Currently, the material scopes and tender documents are being prepared relating to the works connected with the modernisation of unit No. 10. |  |  | 0 | 122.6 | 1% | 2018
of 2 x 500 MW modernisation programme